## Sheet1
Section #: | 4
Team Name: | CtrlAltDelete
Name | Assigned Tasks | Total # of Hours Planned | When is it due?
Elina Grigoryan | Work on prototype/mockup | 3 | 10/8, 11:59 pm
| Schedule and attend follow-up meeting to discuss prototype/mockup draft - email may be the mode of contact depending on client availability | 2 | 10/6, 11:59 pm
| Submit final prototype/mockup after client approval | 0.5 | 10/8, 11:59 pm
| Review project charter and make neccessary changes - Check grading comments - Distribute revised version to the project team | 1 | 10/12, 11:59 pm
| Email the client to arrange a formal review of the Project Charter - Address any questions or concerns of the client - Acquire client signature | 1 | 10/12, 11:59 pm
| Submit signed & revised Project Charter | 0.5 | 10/14, 11:59 pm
| Discuss tech stack - Programming languages, frameworks, databases, front-end/back-end tools, APIs - Consider previous experience of project team | 0.5 | 09/29, 7:00pm
| Attend lab advisor meeting - Brief advisor on project team's progress - Discuss determined tech stack, prototype - Revisit previous topics if neccessary | 1 | 10/02, 8:00pm
Ashley Wisniewski | Work on prototype/mockup | 3 | 10/8, 11:59 pm
| Finalize Prototype/Mockup - Address any modification requests by client | 2 | 10/8, 11:59 pm
| Email the client to review final Prototype/Mockup - Discuss modifications - Request approval | 1 | 10/7, 11:59 pm
| Discuss tech stack - Programming languages, frameworks, databases, front-end/back-end tools, APIs - Consider previous experience of project team | 0.5 | 09/29, 7:00pm
| Attend lab advisor meeting - Brief advisor on project team's progress - Discuss determined tech stack, prototype - Revisit previous topics if neccessary | 1 | 10/02, 8:00pm
John Vardanyan | Work on prototype/mockup | 3 | 10/8, 11:59 pm
| Create Figma - Provide access to project team via email - Review Figma's prototyping features | 0.5 | 10/03, 11:59 pm
| Discuss tech stack - Programming languages, frameworks, databases, front-end/back-end tools, APIs - Consider previous experience of project team | 0.5 | 09/29, 7:00pm
| Attend lab advisor meeting - Brief advisor on project team's progress - Discuss determined tech stack, prototype - Revisit previous topics if neccessary | 1 | 10/02, 8:00pm
Madusha Yakupitiyage | Work on prototype/mockup | 3 | 10/8, 11:59 pm
| Schedule and attend follow-up meeting to discuss prototype/mockup draft - email may be the mode of contact depending on client availability | 2 | 10/6, 11:59 pm
| Discuss tech stack - Programming languages, frameworks, databases, front-end/back-end tools, APIs - Consider previous experience of project team |  | 09/29, 7:00pm
| Attend lab advisor meeting - Brief advisor on project team's progress - Discuss determined tech stack, prototype - Revisit previous topics if neccessary | 1 | 10/02, 8:00pm
Nikolay Chkhaylo | Work on prototype/mockup | 3 | 10/8, 11:59 pm
| Attend requirements meeting - Provide supplementary inquiries as needed | 2 | 10/3, 11:59 pm
| Discuss tech stack - Programming languages, frameworks, databases, front-end/back-end tools, APIs - Consider previous experience of project team | 0.5 | 09/29, 7:00pm
| Attend lab advisor meeting - Brief advisor on project team's progress - Discuss determined tech stack, prototype - Revisit previous topics if neccessary | 1 | 10/02, 8:00pm
Arjun Bhargava | Work on prototype/mockup | 3 | 10/8, 11:59 pm
| Schedule and attend requirements meeting - Contact client via emial - Supply zoom link to project team - Deliver a selection of carefully crafted questions to the client | 3 | 10/3, 11:59 pm
| Discuss tech stack - Programming languages, frameworks, databases, front-end/back-end tools, APIs - Consider previous experience of project team | 0.5 | 09/29, 7:00pm
| Attend lab advisor meeting - Brief advisor on project team's progress - Discuss determined tech stack, prototype - Revisit previous topics if neccessary |  | 10/02, 8:00pm
Navid Baghaei | Work on prototype/mockup | 3 | 10/8, 11:59 pm
| Attend requirements meeting - Relay meeting time to project team - Document requirements - Distribute notes to project team | 3 | 10/3, 11:59 pm
| Discuss tech stack - Programming languages, frameworks, databases, front-end/back-end tools, APIs - Consider previous experience of project team | 0.5 | 09/29, 7:00pm
| Attend lab advisor meeting - Brief advisor on project team's progress - Discuss determined tech stack, prototype - Revisit previous topics if neccessary | 1 | 10/02, 8:00pm
Jeremy Vuong | Work on prototype/mockup | 3 | 10/8, 11:59 pm
| Finalize Prototype/Mockup - Address any modification requests by client | 2 | 10/8, 11:59 pm
| Discuss tech stack - Programming languages, frameworks, databases, front-end/back-end tools, APIs - Consider previous experience of project team | 0.5 | 09/29, 7:00pm
| Attend lab advisor meeting - Brief advisor on project team's progress - Discuss determined tech stack, prototype - Revisit previous topics if neccessary | 1 | 10/02, 8:00pm